## Gantt Chart
PROJECT TITLE |  | EMPLOYEE MANAGEMET SYSTEM
PROJECT MANAGER |  | RONNIE REALCO
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[6 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Project Charter Initiation |  | 2022-12-12 | 2022-12-21 | 100% | bar: WEEK 1 F to WEEK 2 T
1.1.1 | Project Charter Revisions |  | 2022-12-12 | 2022-12-21 | 100% | bar: WEEK 2 W
1.3 | Revised Flowchart |  | 2023-01-30 | 2023-02-06 | 100% | bar: WEEK 2 R to WEEK 3 R
1.4 | Create git Repository |  | 2023-02-06 | 2023-02-20 | 100% | bar: WEEK 3 M to WEEK 3 R
1.5 | Inital Code |  | 2023-02-20 | 2023-02-24 | 100% | bar: WEEK 3 T to WEEK 3 R
1.6 | Instruction |  | 2023-02-20 | 2023-02-24 | 100% | bar: WEEK 3 F
1.7 | Gantt Chart | bar: WEEK 3 F
2 | Employee Management System
2.1 | Add Employee |  |  |  | 100% | bar: WEEK 4 M to WEEK 5 F
2.2 | Search Employee |  |  |  | 100% | bar: WEEK 8 T to WEEK 9 M
2.3 | Edit Employee |  |  |  | 100% | bar: WEEK 6 M to WEEK 6 F
2.4 | Delete Employee |  |  |  | 100% | bar: WEEK 7 M to WEEK 7 F; WEEK 9 T to WEEK 10 M
2.5 | Show all Employee |  |  |  | 100% | bar: WEEK 9 R to WEEK 10 M